## Timeline
Task Name | Duration | Start | Finish | Owner | Comments
Option/coding/syntex/logic summary for K-M related outputs | 8 days | 2024-09-03 | 2024-09-13 | Patrick | Better include outputs and actural codes
Option/coding/syntex/logic summary for Cox model for covariate analysis | 8 days | 2024-09-03 | 2024-09-13 | Zongfeng
Option/coding/syntex/logic summary for test related contents and support KM/Cox | 8 days | 2024-09-03 | 2024-09-13 | Han (Optional:Jason)
Utility macro code drafted | 1 month | 2024-09-13 | 2024-10-26
Display Macro drafted |  | 2024-10-26 | 2024-11-08

## Scope
Table of contents – Oncology efficacy domain
ID | Version | Unique/Repeat within this domain | Based on layout | Numbering as per CSR | Title | Requirement | Owner
AZTONCEF01 | 2 | Unique | AZTBL1b | 14.2.x | Best overall response <<at timepoint>> based on [[confirmed¦unconfirmed]] response by [[blinded independent central review¦independent central review¦investigator assessment]] | Required as per CSP)
AZTONCEF02A | 1 | Unique | AZTEF04 | 14.2.x | [[Objective response¦Response¦Clinical benefit¦Disease control]] rate <<at x weeks>> based on [[confirmed¦unconfirmed]] response by [[blinded independent central review¦independent central review¦investigator assessment]] - [[sensitivity¦supplementary]] analysis - <<Subjects with measurable disease>> | Required as per CSP) | HW
AZTONCEF02B | 1 | Unique | AZTEF04 | 14.2.x | [[Objective response¦Response¦Clinical benefit¦Disease control]] rate <<at x weeks>> based on [[confirmed¦unconfirmed]]response by [[blinded independent central review¦independent central review¦investigator assessment]] - [[sensitivity¦supplementary]] analysis -<<Subjects with measurable disease>> | Required as per CSP) | HW
AZTONCEF03 | 3 | Unique | AZTBL2a | 14.2.x | Duration and onset of [[objective response¦response]] based on [[confirmed¦unconfirmed]] response by [[blinded independent central review¦independent central review¦investigator assessment]] | Required as per CSP)
AZTONCEF04 | 3 | Unique | AZTBL2a | 14.2.x | Progression-free survival by [[blinded independent central review¦independent central review¦investigator assessment]] | Required as per CSP)
AZTONCEF05 | 3 | Unique | AZTEF07 | 14.2.x | [[Progression-free survival¦Overall survival]] by [[blinded independent central review¦independent central review¦investigator assessment]] - [[sensitivity¦supplementary]] analysis | Optional
AZTONCEF06 | 2 | Unique | AZTEF07 | 14.2.x | [[Progression-free survival¦Overall survival]] by [[blinded independent central review¦independent central review¦investigator assessment]] - subgroup analysis | Optional
AZTONCEF07 | 2 | Unique | AZTBL1b | 14.2.x | Treatment status at progression by [[blinded independent central review¦independent central review¦investigator assessment]] | Optional
AZTONCEF08 | 4 | Unique | AZTBL2a | 14.2.x | Time from progression-free survival censoring to data cut off in censored subjects by [[blinded independent central review¦independent central review¦investigator assessment]] | Optional
AZTONCEF09 | 4 | Unique | AZTONCEF04 | 14.2.x | Overall survival | Required as per CSP)
AZTONCEF10 | 4 | Unique | AZTBL2a | 14.2.x | [[Best percentage change from baseline¦Percentage change from baseline at x weeks]] in <<target lesion tumour size>> by [[blinded independent central review¦independent central review¦investigator assessment]] | Optional
AZTONCEF11 | 4 | Unique | AZTBL3b | 14.2.x | [[Change¦Percentage change]] from baseline in <<target lesion tumour size>> over time by [[blinded independent central review¦independent central review¦investigator assessment]] | Optional
AZTONCEF12 | 3 | Unique | AZTBL1b | 14.2.x | New lesions by [[blinded independent central review¦independent central review¦investigator assessment]] | Optional
AZTONCEF13 | 3 | Unique | AZTBL2a | 14.2.x | Concordance of investigator and central review of <<RECIST>> progression including deaths | Optional
AZTONCEF14 | 1 | Unique | AZTONCEF04 | 14.2.x | Time to [[first subsequent therapy¦second subsequent therapy¦IP discontinuation]] or death | Required as per CSP)
AZTONCEF15 | 1 | Unique | N/A | 14.2.x | Global interaction test | Optional
AZTONCEF16 | 1 | Unique | AZTBL2a | 14.2.x | Duration of follow-up (<<unit>>) for [[progression-free survival¦overall survival]] | Optional
AZTONCEF17 | 1 | Unique | AZTONCEF04 | 14.2.x | Second progression-free survival by [[blinded independent central review¦independent central review¦investigator assessment]] | Required as per CSP)

## Macros
Utility macros | Owners | Function
m_u_surv | Patrick
m_u_cox | Zongfeng
m_u_binom_cp | Jason
m_u_binom_odds | Han Wang

## Check scenario and list
Macro Name | Macro Function | Check point or scenario | proposer
m_u_binom_adjrate | utility | Check if the adjusted rate and original rate are consistent when there is no stratification | Han
m_t_binom | display | Check if there are multiple treatment group without sorting properly, will the output be accomplished | Han
m_u_effcount | utility | Check the denominator is set up correctly with denom= parameter
Decimal control for p-value confidence interval
Multiple treatment group
Statistical analysis cover condition

## m_u_km
Core Index | Explanation | Comments | AZTONCEF04 / AZTONCEF09
inds | dataset that contains the time variable, censor variable, and optional class, adjusting variables, and stratification variables.
whr | Gives a where clause to subset the DATA dataset down. Type exactly as would be in a procedure step. Does not change original dataset.
alpha | Determines the alpha for confidence intervals. Default is 0.05.
method | Determines which method is used to generate the curves. Options are KM (Kaplan-Meier) or CIF (Cumulative Incidence Function) ¦ Defaule = KM
conftype | Method of computing confidence intervals for Kaplan-Meier survival estimates. Default is LOG, options are: LOG, ASINSQRT, LOGLOG, LINEAR, LOGIT.
trtgrpn | numerical group variables
trtgrpnord | a list of number to sort 'trtgrpn'
trtgrpn2 | Variable used to subset the CLASS variable further. Will calculate statistics and draw curves within each level of the BY variable. CLASS levels do not have to match between BY levels. Opens ability to calculate interaction p-values between CLASS and BY variables. CLASSORDER and CLASSREF can be specified separately between BY levels.
var_time | Variable containing time to event information ¦ Defaule = AVAL |  | AZTONCEF05
var_status | Numeric variable containing event (coded as a binary variable) ¦ Defaule = CNSR
cen_num | Numeric constant representing value of a non-event in CENS.¦ Default = 0
evnt_num | Numeric constant representing the event of interest in a competing risks analysis. There is no default for this variable. It is only required when method = CIF. | necessary?
step_list | Numeric time-points to collect Kaplan-Meier survival estimates w/confidence intervals. Can be entered as numeric values separated by spaces, or in a list format (example: 0 to 60 by 10). | how to handle timelist like 3,6,12,18
step_unit | Unit of time
xdivisor | Numeric constant to transform the time variable into other units. Will divide the time variable before Kaplan-Meier survival estimates are computed
plot | A flag variable to turn printing the plot off (0) or on (1) ¦ Default = 1 (on), options = 1 (on) or 0 (off).
outdat_median
median_label
Core code: |  | output dataset,naming rule: macro name+step number+selfdefined.
ods output quartiles=quartiles1 ProductLimitEstimates=ple1 CensoredSummary=censored1; |  | median survival: strata vs by | AZTONCEF06
proc lifetest data=&inds. alpha=&alpha. method=&method. outsurv=outsurv1 atrisk timelist=(0 to &maxtime. by &step_by.);; |  | GPP:1. 尽可能少直接替换原来的数据集 2. temp variable name可以命名成_01/_02/_03
by &trtgrpn.;
time &var_time. * &var_status.(&cen_num.);;
run;
Core code (PZ):

## m_u_cox_logrank
Core Index | Explanation | Comments
inds | input dataset
out | output dataset
blocklbl | Create the block column in output dataset (Default is "Comparison of treatment groups")
modelkey | cox: indication to calculate Hazard Ratio and CI using Cox proportional hazards model logrank: indication to calculate p-value using Log-rank Test
transfl | indication to transpose output dataset, with treatment variables (var) as columns. (Default is Y)
popds | population dataset
trtgrpn | treatment variable
var | numeric variable name, should be only one variable, generally set to aval for 'time to event'.
byvar | statistical computing by variable name
alpha | confidence level for confidence limits to calculate 100(1-ALPHA)% confidence limits. (Default is 0.05)
censor | censor variable (Default is cnsr)
indicator | indicator for censor (Default is 1)
ties | method to handle ties in the failure time, includes: BRESLOW DISCRETE EFRON EXACT. (Default is EFRON)
pair | specify sequence of pairs for pairwise statistics, such as: 1-2, then the reference group is 2. (Default is 2-1)
strata | the variables names that determine the strata levels
pvalside | 1-sided or 2 sided p-value, this option only for log-rank test. (Default is 2)
missval | output point estimation when it is not estimable including NC, NE, NA or NR. (Default is NC)
digit | number for HR/CI decimal place. (Default is 2 for HR, 2+1 for CI) Default p-value Rounded to 3 decimal places (eg, "0.xxx"), less than 0.001 is displayed as "<0.001"
cidecimal | To add more decimal place for CI. 1 more decimal place for CI compared to point estimation digit. (Default is 1)
hrlbl | Hazard ratio label (Default is Hazard ratio)
cilbl | CI label as xx% CI, xx determined by alpha (Default is %CI)
pvallbl | pvalue label. (Default is p-value)
prefix | The output dataset column prefix name. (Default is col)
debug | Keep temporary datasets in WORK library if DEBUG = Y. (Default is N)
Core Code:
proc phreg data=&inds alpha=&alpha.;
where &trtvar in (&__pair);
by &byvar;
class &strata. &trtvar.(ref="&__ref.")/param=ref;
model __time*__cnsr(&indicator.)=&trtvar./alpha=&alpha. risklimits RL=both ties=&ties.;
%if %qcmpres(&strata) ne %str() %then %do;
strata &strata.;
%end;
ods output ParameterEstimates=__tmp_hr_estimate;
run;
proc lifetest data=xx
where &trtvar in (&__pair) and missing(__notrt);
by &byvar;
time __time*__cnsr(&indicator.);
%if %qcmpres(&strata) ne %str() %then %do;
strata &strata/test=logrank group=&trtvar;
%end;
%else %do;
strata &trtvar/test=logrank;
%end;
ods output homtests=mu_logrk_homtests_&_p;
run;

## m_u_binom_cp_sin
Core Index | Explanation | Comments
inds | Name of the analysis dataset that is pre-processed.
trtgrpn | Name of the treatment group variable.
group_number | Numeric value of the treatment group that user want to analyze on.
group_name | Treatment group name of the treatment group that user want to analyze on.
ord | Numeric value of the order.
alpha | Alpha level for the confidence interval.
level | Level parameter for the confidence interval. (default to 1)
digit | Decimal place kept for the confidence interval. (default to 1) | order: Order used for proc sort later on
missval | Missing value to display in case confidence interval is unable to be calculated. (default to NC) | col1: Name of treatment group
outds | Name of the output dataset. | col2: Small n and percentage
debug | Y/N on debug. If yes, all temporary datasets will be kept. Otherwise, will be deleted. | col3: Confidence interval
Sub-order: Order for each sub-section
Core code: |  | order: Order used for proc sort later on
proc freq data = anl_3;
by &trtgrpn.;
tables aval / binomial (CL = exact level ='1') alpha = &alpha.;
weight small_n;
run;
Note on B2: [线程批注] 你的Excel版本可读取此线程批注; 但如果在更新版本的Excel中打开文件，则对批注所作的任何改动都将被删除。了解详细信息: https://go.microsoft.com/fwlink/?linkid=870924 注释: Need to define the denom. All population in adsl. or population in adeff.

## m_u_binom_cp_grp
Core Index | Explanation | Comments
inds | Name of the analysis dataset that is pre-processed.
trtgrp | Name of the treatment group variable.
alpha | Alpha level for the confidence interval.
level | Level parameter for the confidence interval. (default to 1)
digit | Decimal place kept for the confidence interval. (default to 1)
missval | Missing value to display in case confidence interval is unable to be calculated. (default to NC)
final_ds | Name of the output dataset.
debug | Y/N on debug. If yes, all temporary datasets will be kept. Otherwise, will be deleted. | order: Order used for proc sort later on
col1: Name of treatment group
Core code: |  | col2: Small n and percentage
%do i = 1 %to &Nobs.; |  | col3: Confidence interval
%m_u_binom_cp_sin(); |  | Sub-order: Order for each sub-section
%end; |  | order: Order used for proc sort later on
Purpose of this macro is to utilize m_u_binom_cp_sin and automatically calculate for all the treatment groups by one macro.
Note on B2: [线程批注] 你的Excel版本可读取此线程批注; 但如果在更新版本的Excel中打开文件，则对批注所作的任何改动都将被删除。了解详细信息: https://go.microsoft.com/fwlink/?linkid=870924 注释: Need to define the denom. All population in adsl. or population in adeff.

## m_u_binom_odds
Core Index | Explanation | Comments
inds | Input dataset
where | Where clause, for setting paramcd and any other flag
popfl | population group
var | aval or other value for event or not
event | Reference event value
trtgrpn | Treatment group number
trtgrp | Treatment group character
trtpair | Treatment comparation pair |  | col5 | col6 | ord | subord | col7 | col0
trtfmt | Treatment format for Treatment group label |  | 0.82 | 0.50, 1.38 | 1 | 1 | 0.46 | Durvalumab
trtref | Treatment reference group number value(Placebo group number) |  |  |  | 1 | 2 |  | N=244
strata | Strata information
alpha | Alpha level
pvalside | P-value sided. 1 or 2.
relcal | Relative risk calculation needed? Default is N, use Y to get relative risk calculation
cltype | Optional defaulted by Miettinen-Nurminen method to calculate the CI
supds | Optional for creating dummy dataset when some treatment or aval is 0
missval | NR,NE,NA. default is NA
ord | Order number or the output dataset.
debug | N/Y
Core code
ods output oddsratiospl = or;
proc logistic data=&inds;
class &strata &trtgrpn / param=glm;
model &var(event="&ref") = &strata &trtgrpn;
oddsratio &trtgrpn / CL=PL;
run;
/*Calculation of Related pvalue:*/
ods output ModelFit=MFTC(where = (criterion="Log Likelihood"));
proc genmod data=&inds;
class &strata &trtgrpn;
model &var(event="&ref") = &strata &trtgrpn / dist=binomial lrci link=logit;
run;
ods output ModelFit=MFC(where = (criterion="Log Likelihood"));
proc genmod data=&inds;
class &strata;
model &var(event="&ref") = &strata / dist=binomial lrci link=logit;
run;
/*For the p value calculate as*/
diff=-2*(MFC.value-MFTC.value);
pval=(1-probchi(diff,1));

## m_u_header
1. m_u_popn中，gmacroN相关的数字是通过_N_计算的，而不是trtgrpn，如果trtgrpn是从2开始，或者自定义99的情况就会有不match的可能，需要重新讨论是否给col赋值数值，从1开始计数_N_

## AZTONCEF01
| AZD1 | AZD2
| <<low dose>> | <<high dose>> | Control
| N=xxx | N=xxx | N=xxx
| n (%) | n (%) | n (%)
Response
Any | x (x.x) | x (x.x) | x (x.x)
<<Complete response>> | x (x.x) | x (x.x) | x (x.x)
<<Partial response>> | x (x.x) | x (x.x) | x (x.x)
<<Response category 1>> | x (x.x) | x (x.x) | x (x.x)
Non-response
Any | x (x.x) | x (x.x) | x (x.x)
<<Stable disease>> | x (x.x) | x (x.x) | x (x.x)
Unconfirmed complete or partial response >= <<x>> weeks | x (x.x) | x (x.x) | x (x.x)
Stable disease >= <<x>> weeks | x (x.x) | x (x.x) | x (x.x)
Non-CR/non-PD >= <<x>> weeks | x (x.x) | x (x.x) | x (x.x)
<<Not evaluable>> | x (x.x) | x (x.x) | x (x.x)
Unconfirmed complete or partial response < <<x>> weeks
Stable disease < <<x>> weeks | x (x.x) | x (x.x) | x (x.x)
Non-CR/non-PD < <<x>> weeks
No baseline or post baseline <<RECIST>> assessments in the absence of death | x (x.x) | x (x.x) | x (x.x)
<<No evidence of disease>> | x (x.x) | x (x.x) | x (x.x)
<<Progression>> | x (x.x) | x (x.x) | x (x.x)
<<RECIST>> progression | x (x.x) | x (x.x) | x (x.x)
Death without <<RECIST>> progression | x (x.x) | x (x.x) | x (x.x)

## AZTONCEF02A
| Subjects with [[objective response¦response¦clinical benefit¦disease control]] | Adjusted rate (%) |  | Comparison of treatment groups
Group | Number (%) | Estimate | <<x>>% CI | Odds ratio | <<x>>% CI | p-value
AZD1 <<low dose>> N=xxx | xx (xx.x) | xx.x | x.x, x.x | x.x | x.x, x.x | 0.xxx
AZD2 <<high dose>> N=xxx | xx (xx.x) | xx.x | x.x, x.x | x.x | x.x, x.x | 0.xxx
Control N=xxx | xx (xx.x) | xx.x | x.x, x.x
…

## AZTONCEF02B
Index
AZTONCEF02B based on AZTEF04
Table 14.2.x
[[Objective response¦Response¦Clinical benefit¦Disease control]] rate <<at x weeks>> based on [[confirmed¦unconfirmed]]response by [[blinded independent central review¦independent central review¦investigator assessment]] - [[sensitivity¦supplementary]] analysis (Full analysis set)
<<Subjects with measurable disease>>
<<Page by values>>
|  |  | Subjects with [[objective response¦response¦clinical benefit¦disease control]] |  | Comparison of treatment groups [b]
[5 empty] | Relative risk |  | Risk difference
|  | Group | Number (%) | <<x>>% CI [a] | Estimate | <<x>>% CI | Estimate | <<x>>% CI | p-value
|  | AZD1 <<low dose>> | xx (xx.x) | x.x, x.x | xx.x | xx.x, xx.x | xx.x | xx.x, xx.x | 0.xxx
N=xxx
|  | AZD2 <<high dose>> | xx (xx.x) | x.x, x.x | xx.x | xx.x, xx.x | xx.x | xx.x, xx.x | 0.xxx
N=xxx
|  | Control | xx (xx.x) | x.x, x.x
N=xxx
…
[a] The confidence interval for [[objective response¦response¦clinical benefit¦disease control]] rate is derived based on <<Clopper-Pearson method>>.
[b] The relative risk and/or risk difference and corresponding <<x>>% confidence interval(s) are presented using the <<Miettinen-Nurminen approach>>. Conditional footnote.
A relative risk [[greater than 1¦below 1]] choose what applies favours <<group name>>. Conditional footnote.
A [[positive¦negative]] choose what applies risk difference favours <<group name>>. Conditional footnote.
The p-value is based on the Cochran–Mantel–Haenszel (CMH) test, stratified by <<factor>> and <<factor>>
CI Confidence interval; n Number of subjects in analysis; N Number of subjects per treatment group; <<RECIST Response evaluation criteria in solid tumors, Version x.x>>. Add version.
Note:
For non RECIST endpoints, footnote can be updated for non RECIST evaluation criteria and version. Abbreviations in footnote to be ordered alphabetically as per General Principles.
Hematology studies use terminology 'Response rate' instead of 'Objective response rate'.

## AZTONCEF03
Index
AZTONCEF03 based on basic layout AZTBL2a
Table 14.2.x
Duration and onset of [[objective response¦response]] based on [[confirmed¦unconfirmed]] response by [[blinded independent central review¦independent central review¦investigator assessment]] (Full analysis set)
<<Page by values>>
|  |  |  | AZD1 | AZD2
|  |  |  | <<low dose>> | <<high dose>> | Control
|  |  | Statistic | N=xxx | N=xxx | N=xxx
|  | Subjects with response | n (%) | xx (xx.x) | xx (xx.x) | xx (xx.x)
|  | Responders who subsequently progressed or died [a] | n (%) | xx (xx.x) | xx (xx.x) | xx (xx.x)
|  | <<RECIST>> progression | n (%) | xx (xx.x) | xx (xx.x) | xx (xx.x)
|  | Death without progression | n (%) | xx (xx.x) | xx (xx.x) | xx (xx.x)
|  | Duration of response (<<unit>>) [b][c] | n | xx | xx | xx
|  |  | P25 | xx.x | xx.x | xx.x
|  |  | Median | xx.x | xx.x | xx.x
|  |  | <<x>>% CI | x.x, x.x | x.x, x.x | x.x, x.x
|  |  | P75 | xx.x | xx.x | xx.x
|  |  | P<<x>> | xx.x | xx.x | xx.x
Percentage remaining in response [b]
|  | <<xx months>> | % | xx.x | xx.x | xx.x
|  |  | 95% CI | x.x, x.x | x.x, x.x | x.x, x.x
|  |  | <<x>>% CI | x.x, x.x | x.x, x.x | x.x, x.x
|  | <<xx months>> | % | x.x | x.x | x.x
|  |  | 95% CI | x.x, x.x | x.x, x.x | x.x, x.x
|  |  | <<x>>% CI | x.x, x.x | x.x, x.x | x.x, x.x
|  | Time to onset of response from | n | xx | xx | xx
|  | [[randomisation¦first dose]] (<<unit>>) | Min | xx | xx | xx
|  |  | Q1 | xx.x | xx.x | xx.x
|  |  | Median | xx.x | xx.x | xx.x
|  |  | Q3 | xx.x | xx.x | xx.x
|  |  | Max | xx | xx | xx
Time to response [a]
|  | <<xx months>> | n (%) | xx (xx.x) | xx (xx.x) | xx (xx.x)
|  | <<xx months>> | n (%) | xx (xx.x) | xx (xx.x) | xx (xx.x)
[a] Denominator is the number of subjects with response.
[b] The calculation is based on the Kaplan-Meier technique.
[c] The confidence interval for median duration of response is derived based on Brookmeyer-Crowley method.
CI Confidence interval; Conditional footnote. n Number of subjects in analysis for a continuous variable and number of subjects per category for a categorical variable; N Number of subjects per treatment group; P25 25th percentile; P75 75th percentile; P<<x>> <<x>>th percentile; Q1 First quartile; Q3 Third quartile; <<RECIST Response evaluation criteria in solid tumors, Version x.x>>. Add version.
Note:
For non RECIST endpoints, responder category for progression can be replaced and footnote updated for non RECIST evaluation criteria and version. Abbreviations in footnote to be ordered alphabetically as per General Principles.
Hematology studies use terminology 'Response' instead of 'Objective response'.

## AZTONCEF04
|  | AZD1 | AZD2
|  | <<low dose>> | <<high dose>> | Control
| Statistic | N=xxx | N=xxx | N=xxx
Event [a]
Any | n (%) | x (x.x) | xx (xx.x) | x (x.x)
<<RECIST>> progression | n (%) | x (x.x) | xx (xx.x) | x (x.x)
Target lesions [b] | n (%) | x (x.x) | xx (xx.x) | x (x.x)
Non target lesions [b] | n (%) | x (x.x) | xx (xx.x) | x (x.x)
New lesions [b] | n (%) | x (x.x) | xx (xx.x) | x (x.x)
Death without progression | n (%) | x (x.x) | xx (xx.x) | x (x.x)
Censored observations
Any | n (%) | x (x.x) | xx (xx.x) | x (x.x)
Censored at Day 1 | n (%) | x (x.x) | xx (xx.x) | x (x.x)
Censored <<RECIST>> progression or death [c] | n (%) | x (x.x) | xx (xx.x) | x (x.x)
Progression-free [d] | n (%) | x (x.x) | xx (xx.x) | x (x.x)
Prematurely censored | n (%) | x (x.x) | xx (xx.x) | x (x.x)
Progression-free at time of the analysis | n (%) | x (x.x) | xx (xx.x) | x (x.x)
Early study discontinuation | n (%) | x (x.x) | xx (xx.x) | x (x.x)
Lost to follow-up | n (%) | x (x.x) | xx (xx.x) | x (x.x)
Withdrew consent | n (%) | x (x.x) | xx (xx.x) | x (x.x)
<<category>> | n (%) | x (x.x) | xx (xx.x) | x (x.x)
Progression-free survival | P25 | x.x | x.x | x.x
(<<unit>>) [e] [f] | Median | xx.x | xx.x | xx.x
| <<x>>% CI | x.x, x.x | x.x, x.x | x.x, x.x
| P75 | x.x | x.x | x.x
| P<<x>> | x.x | x.x | x.x
Comparison of treatment groups [g] | Hazard ratio | x.x | x.x
| <<x>>% CI | x.x, x.x | x.x, x.x
| <<x>>% CI | x.x, x.x | x.x, x.x
| p-value | 0.xxx | 0.xxx
Progression-free survival rate [e]
<<xx months>> | % | xx.x | xx.x | xx.x
| <<x>>% CI | x.x, x.x | x.x, x.x | x.x, x.x
…
<<xx months>> | % | xx.x | xx.x | xx.x
| <<x>>% CI | x.x, x.x | x.x, x.x | x.x, x.x
…
Missed two or more consecutive | n (%) | x (x.x) | xx (xx.x) | x (x.x)
<<RECIST>> assessments
Duration between <<RECIST>> progression | n | x | x | x
and the last evaluable <<RECIST>> | Min | xx.x | xx.x | xx.x
assessment prior to progression (<<unit>>) | Q1 | x.x | x.x | x.x
| Median | xx.x | xx.x | xx.x
| Q3 | xx.x | xx.x | xx.x
| Max | xx | xx | xx

## AZTONCEF09
Index
AZTONCEF09 based on layout AZTONCEF04
Table 14.2.x
Overall survival (Full analysis set)
<<Page by values>>
|  |  |  | AZD1 | AZD2
|  |  |  | <<low dose>> | <<high dose>> | Control
|  |  | Statistic | N=xxx | N=xxx | N=xxx
Event
|  | Death | n (%) | xx (x.x) | xx (xx.x) | xx (x.x)
Censored observations
|  | Any | n (%) | xx (x.x) | xx (xx.x) | xx (x.x)
|  | Still in survival follow-up [a] | n (%) | x (x.x) | xx (xx.x) | x (x.x)
|  | Early study discontinuation | n (%) | x (x.x) | xx (xx.x) | x (x.x)
|  | Lost to follow-up | n (%) | x (x.x) | xx (xx.x) | x (x.x)
|  | Withdrew consent | n (%) | x (x.x) | xx (xx.x) | x (x.x)
|  | <<category>> | n (%) | x (x.x) | xx (xx.x) | x (x.x)
|  | Overall survival (<<unit>>) [b] [c] | n | xx | xx | xx
|  |  | P25 | x.x | x.x | x.x
|  |  | Median | xx.x | xx.x | xx.x
|  |  | <<x>>% CI | x.x, x.x | x.x, x.x | x.x, x.x
|  |  | P75 | x.x | x.x | x.x
|  |  | P<<x>> | x.x | x.x | x.x
|  | Comparison of treatment groups [d] | Hazard ratio | x.x | x.x
|  |  | <<x>>% CI | x.x, x.x | x.x, x.x
|  |  | <<x>>% CI | x.x, x.x | x.x, x.x
|  |  | p-value | 0.xxx | 0.xxx
Overall survival rate [b]
|  | <<xx months >> | % | xx.x | xx.x | xx.x
|  |  | <<x>>% CI | x.x, x.x | x.x, x.x | x.x, x.x
…
|  | <<xx months >> | % | xx.x | xx.x | xx.x
|  |  | <<x>>% CI | x.x, x.x | x.x, x.x | x.x, x.x
…
…
[a] Includes subjects not known to have died on or before DCO date.
[b] The calculation is based on the Kaplan-Meier technique.
[c] The confidence interval for median overall survival is derived based on Brookmeyer-Crowley method.
[d] The analysis is performed using <<method/model>> as described in the statistical analysis plan. A hazard ratio below 1 favours <<group name>>. The p-value is based on the stratified log-rank test. Conditional footnote, if not already given in the model description. The p-value reflects the <<x>>-sided <<test>> Include name of the test and the significance level. Conditional footnote. The p-value is adjusted using <<methods>> Conditional footnote
CI Confidence interval; DCO Data cut-off; n Number of subjects in analysis; N Number of subjects per treatment group; P25 25th percentile; P75 75th percentile; P<<x>> <<x>>th percentile; Q1 First quartile; Q3 Third quartile.
Note:
Death, still in survival follow-up are mutually exclusive.

## AZTONCEF14
|  | AZD1 | AZD2
|  | <<low dose>> | <<high dose>> | Control
| Statistic | N=xxx | N=xxx | N=xxx
Event [a]
Any | n (%) | xx (x.x) | xx (xx.x) | xx (xx.x)
Time to [[first subsequent therapy¦ | P25 | x.x | x.x | x.x
second subsequent therapy¦ | Median | xx.x | xx.x | xx.x
IP discontinuation]] or death (<<unit>>) [b] [c] | <<x>>% CI | x.x, x.x | x.x, x.x | x.x, x.x
| P75 | x.x | x.x | x.x
| P<<x>> | x.x | x.x | x.x
Comparison of treatment groups [d] | Hazard ratio | x.x | x.x
| <<x>>% CI | x.x, x.x | x.x, x.x
| p-value | 0.xxx | 0.xxx
Time between progression and starting | n | xx | xx | xx
[[first¦second]] subsequent therapy | Min | x | x | x
(<<unit>>) | Q1 | x.x | x.x | x.x
| Median | xx.x | xx.x | xx.x
| Q3 | xx.x | xx.x | xx.x
| Max | xx | xx | xx
Best overall response to [[first¦second]] subsequent therapy
Any | n (%) | xx (x.x) | xx (xx.x) | xx (xx.x)
<<Complete response>> | n (%) | xx (x.x) | xx (xx.x) | xx (xx.x)
<<Partial response>> | n (%) | xx (x.x) | xx (xx.x) | xx (xx.x)
<<Response category 1>> | n (%) | xx (x.x) | xx (xx.x) | xx (xx.x)
… | …

## AZTONCEF17
Index
AZTONCEF17 based on AZTONCEF04
Table 14.2.x
Second progression-free survival by [[blinded independent central review¦independent central review¦investigator assessment]] (Full analysis set)
<<Page by values>>
|  |  |  | AZD1 | AZD2
|  |  |  | <<low dose>> | <<high dose>> | Control
|  |  | Statistic | N=xxx | N=xxx | N=xxx
Event
|  | Any | n (%) | x (x.x) | xx (xx.x) | x (x.x)
|  | Second progression | n (%) | x (x.x) | xx (xx.x) | x (x.x)
|  | Objective radiological progression | n (%) | x (x.x) | xx (xx.x) | x (x.x)
|  | Symptomatic progression | n (%) | x (x.x) | xx (xx.x) | x (x.x)
|  | … | n (%) | x (x.x) | xx (xx.x) | x (x.x)
|  | Death without second progression | n (%) | x (x.x) | xx (xx.x) | x (x.x)
Censored observations
|  | Any | n (%) | x (x.x) | xx (xx.x) | x (x.x)
|  | No first progression in the absence of death | n (%) | x (x.x) | xx (xx.x) | x (x.x)
|  | Subsequent therapy after first progression | n (%) | x (x.x) | xx (xx.x) | x (x.x)
|  | Subsequent therapy after first progression without second progression assessment | n (%) | x (x.x) | xx (xx.x) | x (x.x)
|  | No subsequent therapy after first progression | n (%) | x (x.x) | xx (xx.x) | x (x.x)
|  | Second progression-free survival | P25 | x.x | x.x | x.x
|  | (<<unit>>) [a] [b] | Median | xx.x | xx.x | xx.x
|  |  | <<x>>% CI | x.x, x.x | x.x, x.x | x.x, x.x
|  |  | P75 | x.x | x.x | x.x
|  |  | P<<x>> | x.x | x.x | x.x
|  | Comparison of treatment groups [c] | Hazard ratio | x.x | x.x
|  |  | <<x>>% CI | x.x, x.x | x.x, x.x
|  |  | <<x>>% CI | x.x, x.x | x.x, x.x
|  |  | p-value | 0.xxx | 0.xxx
Progression-free survival rate [a]
|  | <<xx months>> | % | xx.x | xx.x | xx.x
|  |  | <<x>>% CI | x.x, x.x | x.x, x.x | x.x, x.x
…
|  | <<xx months>> | % | xx.x | xx.x | xx.x
|  |  | <<x>>% CI | x.x, x.x | x.x, x.x | x.x, x.x
…
[a] The calculation is based on the Kaplan-Meier technique.
[b] The confidence interval for median progression-free survival is derived based on Brookmeyer-Crowley method.
[c] The analysis is performed using <<method/model>> as described in the statistical analysis plan. A hazard ratio <<below 1>> favours <<group name>>.
The p-value is based on the stratified log-rank test. Conditional footnote, if not already given in the model description. The p-value reflects the <<x>>-sided <<test>> Include name of the test and the significance level. Conditional footnote. The p-value is adjusted using <<methods>> Conditional footnote
CI Confidence interval; n Number of subjects in analysis; N Number of subjects per treatment group; P25 25th percentile; P75 75th percentile; P<<x>> <<x>>th percentile; <<RECIST Response evaluation criteria in solid tumors, Version x.x>>. Add version.
Note:
For non RECIST endpoints, event category for progression can be replaced and footnote updated for non RECIST evaluation criteria and version.
Re-order footnotes if optional categories are not presented. Abbreviations in footnote to be ordered alphabetically as per General Principles.